## Sheet2
Project Name: | Easy Meals - Campus Mni Food Court
Team 4: | Deepthi,Dharani,Priya and Mahitha
Objectives: | To ensure clear, consistent, and timely communication across all stakeholders to support project success.
Communication Management Matrix
Communication Activites | Methods | Objectives | Owners | Audience | Frequency | Type
Project Sponsor | Executive Summary via Webex | Budget, timeline, risks | Project Manager | Project Sponsor/ Dean/ Administration | Biweekly | Interactive
Facilities & Operations | Shared Drive | Layout updates, utilities schedule | Project Manager / Facilities Lead | Facilities and Operations | Weekly (Tuesdays) | Push
Vendors | Webex | Contract requirements, approvals | Vendor Coordinator | Vendor and Local businesses | Weekly | Interactive
Project Team | Group Chat via Teams, Weekly Webex | Tasks, updates | Project Manager | Project internal team | Twice Weekly | Interactive
Finance Department | Shared Folder | Purchase orders, vendor payments | Project Manager and Finance Rep | Finance Department | As Needed | Pull
Student & Faculty Community | Posters, Social Media, Campus Emails | Awareness, launch updates | Marketing Lead | Marketing/ Student Affairs | Biweekly | Push
University Admin | Dashboard/ Reports | Project summary, KPIs | Project Manager | University Community | Monthly | Push