## Sheet1
Risk Description | Initial Probability (1-5) | Initial Impact (1-5) | Initial Risk Score | Risk Response | Residual Probability (1-5) | Residual Impact (1-5) | Residual Risk Score | Responsible Role | Last Update | Date | Current Status
Bad weather delays vendor deliveries | 2 | 3 | 6 | Use local suppliers; build small buffer stock for non-perishables | 2 | 2 | 4 | Vendor Manager
Campus policy change restricting food sales | 1 | 4 | 4 | Maintain regular communication with adminstration; prepare backup plan for packaged items only. | 1 | 3 | 3 | Project Sponsor/ Univerisity Liaison | Sponsor checked with university adminstration | 2025-09-15 | On Watch
Cost overruns from underestimated materials | 3 | 3 | 9 | keep 15% contingency reserve; monitor weekly expenses | 2 | 3 | 6 | Finance Lead | Reviewed material costs and confirmed contigency still valid | 2025-09-30 | Open Risk
Delay in obtaining university space approval | 4 | 5 | 20 | Begin approval process early; hold weekly meetings with Facilities. | 3 | 4 | 12 | Project Manager | Held follow up meeting with Facilities | 2025-10-05 | Open Risk
Delay in utility setup (water,power,Wi-Fi) | 3 | 4 | 12 | Submit Facilities work orders early, include 2 week schedlue buffers | 2 | 3 | 6 | Facilities Coordinator | Received tentative utility completion schedule | 2025-10-15 | Open Risk
Equipment malfunction (microwaves, water stations) | 2 | 3 | 6 | Perform weekly maintenance, keep one spare unit, label repair contact clearly. | 2 | 2 | 4 | Facilities Lead/ Maintenance Supervisor
Health or food safety inspection failure | 3 | 5 | 15 | Conduct internal audit; ensure vendors have valid food handling certifications | 2 | 4 | 8 | Operations Lead | Verfied vendor certifications | 2025-10-23 | Open Risk
Hygiene/ Poor food quality | 3 | 3 | 9 | Weekly quality checks; student feedback QR codes | 2 | 3 | 6 | Quality Assurance (QA)Lead
Low student turnout during pilot | 2 | 4 | 8 | Run marketing campaign, launch event, free tasting days | 3 | 3 | 9 | Marketing Lead | Launched awareness campaign | 2025-10-29 | Open Risk
Project ends without capturning performance metrics | 2 | 4 | 8 | Assisgn a data lead; track sales, surveys and vendor satisfaction weekly. | 2 | 2 | 4 | Project Manager/Data Analyst
Team buronout during setup phase | 3 | 3 | 9 | Rotate work schedules; limit overtime; reward team milestones. | 2 | 2 | 4 | Project Manager | Implemented shift rotations | 2025-10-30 | Mitigated
Vendor conflicts | 1 | 3 | 3 | Set vendor rules for space/time slots; host orientation | 2 | 2 | 4 | Vendor Coordinator | Reviewed vendor schedule alignment | 2025-11-01 | Open Risk
Vendor withdrawal before launch | 3 | 4 | 12 | Have backup vednor list; use flexible, short term trial contacts. | 2 | 3 | 6 | Procurement Lead | Confirmed backup vendor contract readiness | 2025-11-01 | Open Risk