## Budget
Project Title: Downtown DineHub
Team: Deepthi,Dharani,Priya and Mahitha
Category | Description | Cost
Space Setup | Minor repairs, setup, and initial utility needs to make the space usable for the pilot. | 4567.1
Furniture | ables, chairs, and small fixtures to seat ~20–30 guests in the food court area. | 7500
equipments | Shared customer microwaves for reheating food safely during pilot hours. | 750
signage | Posters, directional signs, and area branding to guide foot traffic to DineHub. | 1219.1
Technology | Card readers, tablets/printers, software licenses, and network drops for secure transactions. | 3498.5
Permits and Insurance | University and local requirements to operate food vendors safely and compliantly. | 1932.18
Supplies | Initial stock of cleaning agents, wipes, gloves, and liners for daily sanitation. | 812.65
Marketing | Simple launch campaign (posters/social/email) to drive awareness and early footfall. | 2456.12
Operations | Additional utilities and custodial services attributable to the pilot. | 4335.47
Staff Support | Time for vendor onboarding, site oversight, surveys, and basic reporting. | 2986.99
Direct costs | Subtotal | 30058.11
Contingency (12%) | For known risks | 3606.9732
Cost Baseline | Direct costs + Contingency | 33665.0832
Management Reserve (5%) | For unknown risks | 1683.2542
Total Project Budget | Grand Total | 35348.3374

## Total
Week | Milestone | Expected spend
Week 3 | Charter approval and permits | 492.13
Week 4 | Space prep starts | 2499.45
Week 6 | Vendor selection and baseline approval | 3890.3
Week 7 | POS/network ordered | 2511.7
Week 8 | Setup and furniture install | 10650
Week 9 | Signage and marketing | 2700
Week 10 | Launch | 875
Week 11-13 | Operations and monitoring | 4500
Contingency + Management Reserve | Risk Buffers | 5290.2274
Total |  | 33408.8074