## Sheet1
Risk ID | Risk Description | Category | Probability | Impact | Risk Score (P×I) | Response Strategy | Mitigation / Response Actions | Owner
R1 | Delay in obtaining university space approval due to bureaucracy | Organizational / Schedule | High | High | 9 | Avoid/Mitigate | Submit proposal early, meet with facilities & admin to pre-align approvals. | Project Manager
R2 | Vendor withdrawal before pilot launch due to low expected sales | Procurement | Medium | High | 6 | Mitigate/Transfer | Sign backup vendors; short-term trial contracts; include termination clause. | Procurement Lead
R3 | Health and safety non-compliance found during inspection | Compliance / Legal | Low | High | 3 | Avoid/Mitigate | Conduct internal safety audit before inspection; coordinate with campus health dept. | Operations Lead
R4 | Low student turnout resulting in poor sales | Market / Stakeholder | High | High | 9 | Mitigate/Accept | Run awareness campaign; offer discounts; host launch event. | Marketing Lead
R5 | Delay in setting up water or electrical utilities for vendors | Technical / Infrastructure | Medium | High | 6 | Mitigate | Engage facilities early; secure installation timeline; include contingency days. | Facilities Coordinator
R6 | Cost overrun due to underestimated setup materials | Financial | Medium | Medium | 4 | Mitigate | Keep 15% contingency reserve; monitor spending weekly; vendor cost-sharing options. | Finance Lead
R7 | Vendor food quality complaints from students | Reputation / Quality | Medium | Medium | 4 | Mitigate | Implement weekly quality checks and feedback surveys; remove underperforming vendors. | QA Lead
R8 | Equipment malfunction (microwave, water dispenser) | Operational | Medium | Medium | 4 | Accept/Mitigate | Label maintenance contacts; perform weekly checks; keep spare microwave unit. | Facilities
R9 | Weather-related delays in vendor food delivery | External | Low | Medium | 2 | Accept | Encourage local suppliers; plan backup storage for non-perishables. | Vendor Manager
R10 | Project closure without measurable feedback or KPIs | Management / Communication | Medium | Medium | 4 | Avoid | Assign metrics lead to track satisfaction, sales, and vendor feedback; final report. | Project Manager
R11 | Security or theft incidents in food court area | Security | Low | High | 3 | Mitigate | Install cameras; coordinate with campus security; post visible signage. | Campus Security Liaison
R12 | Vendor conflicts or competition between local businesses | Stakeholder / Relationship | Medium | Medium | 4 | Mitigate | Host vendor orientation; establish clear ground rules for shared space. | Vendor Coordinator
R13 | Insufficient waste management leading to hygiene complaints | Environmental / Compliance | Medium | High | 6 | Mitigate | Place visible waste bins; schedule daily cleaning with facilities. | Operations Lead
R14 | Change in university policies restricting food sales | Regulatory | Low | High | 3 | Accept | Maintain communication with admin; adjust project operations accordingly. | Project Sponsor
R15 | Team burnout during high-pressure setup weeks | Human Resources | Medium | Medium | 4 | Mitigate | Rotate shifts; provide recognition and breaks; track workload. | Project Manager