Project TITLE - Project Management Plan

GRoup 4: DOWNTOWN DINEHUB

Date	12/03/2025

Table of Contents

# Project Executive Summary…………………………………………………………………..1

# Project Governance……………………………………………………………………………1

# Project Stakeholder Management Plan……………………………………………..………..1

# Scope Management Plan………………………………………………………………………2

# Communication Plan…………………………………………………………………………..2

# Change Management Plan………………………………………………………………….....2

# Project Change Classification…………………………………………………………………2

# Risk Management Plan………………………………………………………………..……….3

# Project Schedule………………………………………………………………..………………4

# Quality Management Plan: ……………………………………………………………………4

# Project Executive Summary:

The Downtown DineHub initiative aims to create a compact, on-campus food court to improve the limited dining choices at the UAlbany Downtown Campus. The project seeks to ensure easy meal access for students and faculty by utilizing available unused space and collaborating with local vendors on a rotating basis. The semester-long pilot will evaluate demand, enhance campus satisfaction, and assess if the model can grow moving forward

# Project Governance:

The DineHub initiative will utilize a predictive management strategy with defined supervision and regulated implementation. A Steering Committee—including Auxiliary Services, Facilities, ITS, Procurement, and EH&S—will direct significant decisions. The Change Control Board (CCB) will assess and authorize any modifications impacting scope, timeline, or budget.

The Project Manager will supervise daily tasks, monitor progress, handle risks, and update stakeholders, while functional leads execute duties in their specific domains. This framework guarantees effective decision-making, uniform communication, and conformity with university standards during the project.

# Project Stakeholder Management Plan:

Key Stakeholders
Students and faculty, Auxiliary Services, Facilities, ITS, EH&S, Procurement, local vendors, and University Administration.

Stakeholder Concerns

- Students/faculty: access to convenient, affordable food with reasonable wait times.

- Auxiliary Services: vendor performance and policy compliance.

- Facilities: space setup and ongoing maintenance.

- ITS: stable POS and network support.

- EH&S: safety, sanitation, and food-handling standards.

- Procurement: correct onboarding and contract processes.

- Vendors: clear expectations and adequate sales.

- Administration: overall project success and campus impact.

Key Considerations for the Team
Students and faculty drive demand, internal departments have required approvals that affect timing, vendors may need simple guidance, and administration expects steady updates.

Engagement Approach
The team will hold regular check-ins with key departments, provide structured onboarding for vendors, collect user feedback during the pilot, send bi-weekly updates to leadership, and escalate major concerns to the Steering Committee.

# Scope Management Plan:

The DineHub project scope will be defined in the Project Charter and detailed in the BRD, covering vendor setup, seating, equipment, and POS needs. Scope will be controlled through a baseline and tracked using the WBS. Any scope changes will require a formal request, reviewed by the Project Manager and escalated to the CCB if they affect time, cost, or major deliverables. Final scope approval will come from Auxiliary Services, Facilities, ITS, and EH&S. All changes will be logged and approved before being implemented to ensure the project stays aligned with its objectives.

# Communication Plan:

Project communication will focus on timely, clear updates to all stakeholders. The project team will meet weekly to review progress and address risks. Facilities, ITS, EH&S, and Auxiliary Services will receive bi-weekly status updates, while vendors will receive weekly check-ins during onboarding and early operations.

Status updates will be shared through email, brief meetings, or shared documents based on stakeholder needs. All project changes will be communicated through documented notices and shared with the CCB when required. The Project Manager will oversee all communication and ensure the Steering Committee is informed of major issues and milestones. This structure supports transparency, alignment, and effective decision-making throughout the project.

# Change Management Plan:

All DineHub project changes will follow a structured review and approval process. Any stakeholder may submit a change request outlining the change and its impact. The Project Manager will review each request first—minor changes may be approved directly, while any change affecting cost, schedule, or major deliverables will be escalated to the Change Control Board (CCB) for tiered approval. Approved changes will be logged in the change register, added to the project plan, and communicated to the relevant stakeholders. The Project Manager will update scope and schedule documents as needed to reflect approved changes.

# Project Change Classification:

- There will be three tiers of project changes, Critical, Major, and Minor.

| Type of Change | General Description | Criteria | Approver | Change request required |
| --- | --- | --- | --- | --- |
| Critical | Major change that significantly impacts DineHub’s scope, schedule, or budget | - Adding major new requirements (e.g., additional vendors, new equipment needs) - Schedule delays over 15 days affecting launch date - Budget increase over 5% - Requires 3 or more additional staff/resources - Any change triggered by a safety or EH&S compliance issue | Steering Committee by consensus | Yes |
| Major | A change that impacts project planning or execution. | - Moderate requirement changes - Delays under 15 days - Budget impact under 5% - Needs <2 extra resources | Change control board by majority | Yes |
| Minor | Routine change with little to no impact on DineHub deliverables | - No change to overall milestones - No added costs - No significant resource impact (e.g., moving seating, adjusting signage wording) | Project Manager | No, but documented change will be emailed to CCB |

# Risk Management Plan:

Project risk plans describe how the project will approach managing risks throughout the lifecycle. This includes how risks will be identified, analyzed, approached, and monitored.

A tiered risk approach is encouraged.

| Category | Score | Control | Risk Acceptance Authority |
| --- | --- | --- | --- |
| Low | 0-5 | Record the risk in the DineHub risk register and keep an eye on it during weekly team check-ins. This applies to small items like quick vendor questions, minor signage tweaks, or short POS downtime. | Project team lead |
| Medium | 6-12 | Log the risk and put mitigation steps in place to reduce it. Escalate the issue if it begins affecting vendor readiness, space preparation, or compliance. | Team Lead or Steering Committee |
| High | 13-25 | Record the risk and escalate it to the Steering Committee for review and approval before action. | Steering Committee |

# Project Schedule:

### Milestones

- Project Kickoff: Week 1

- Vendor Contracts Finalized: Week 5

- POS Ready for Use: End of Week 6

- Marketing Released: Week 7

- Pilot Launch: Week 10

- Final Evaluation Submitted: Week 14\

| Phase | Timeline (Weeks) | Key Activities |
| --- | --- | --- |
| Space Preparation | Weeks 1–3 | Finalize location, minor setup, utilities check, seating layout, signage planning |
| Vendor Onboarding | Weeks 3–5 | Vendor selection, contracts, EH&S review, menu approvals, onboarding sessions |
| POS Setup & Technology Testing | Week 6 | Install POS equipment, connect to ITS systems, perform functionality and load testing |
| Marketing & Awareness Campaign | Weeks 7–9 | Launch promotional materials, campus communications, vendor introductions |
| Pilot Launch | Week 10 | Open DineHub to students and faculty; monitor first-week operations |
| Monitoring & Adjustments | Weeks 11–13 | Track transactions, gather feedback, ensure vendor performance, address issues |
| Final Evaluation & Closeout | Week 14 | Compile results, feedback, and recommendations. |

# Quality Management Plan:

The DineHub project will use a structured quality process to ensure space setup, vendor readiness, POS functionality, and safety standards meet university expectations before launch.

### Testing Types

- Functional: POS performance, network stability, and transactions

- Operational: Vendor setup, equipment checks, seating layout, and workflow

- Safety & Compliance: EH&S inspections, food safety, sanitation, and ADA requirements

### Responsibilities

- ITS: POS and technical testing

- EH&S: Safety and sanitation checks

- Facilities: Space and equipment readiness

- Auxiliary Services & PM: Vendor onboarding and overall readiness

### Tracking & Validation

Quality issues will be logged and reviewed weekly. Major issues that affect scope or schedule will be escalated to the CCB. Each team will create its own checklists, which the Project Manager will consolidate into a final readiness checklist. Functional leads will validate test results, and any safety-related changes must be approved by EH&S.

This approach ensures DineHub launches safely and operates reliably for students and faculty.