## Sheet1
Project Name: |  | Downtown DineHub |  |  |  | Project Manager: |  | Team 4
Stakeholder Name |  |  | Project Role | Influence* | Key Interests |  | Interest Level |  | Communication Method | Frequency
University at Albany |  |  | Provides funding, approves scope, and expects measurable ROI and student satisfaction | High | Ensuring high customer satisfaction, financial return on investement, and enchanced student experience |  | High |  | Progress reports, review meetings, and formal email updates | Weekly
Auxiliary Services |  |  | Oversees food operations,vendor performance, and service quality | High | Maintaining smooth operations and consistent vendor quality |  | High |  | Coordination meetings, operational dashboards, and direct calls | Weekly
Procurement Office |  |  | Manages vendor contracts and compliance with university policy | High | Contract approval,vendor selection, and procurement timelines |  | Medium |  | Contact review meetings and document updates via email | Bi-weekly
Facilities Department |  |  | Prepares space, utilities, seating, and maintenance support | Med | Completing setup on time and meeting safety and accessibility standards |  | Medium |  | Site inspections, maintenance updates, and team calls | Weekly
Environmental Health & Safety (EH&S) |  |  | Ensures compliance with health and food safety standards | High | Sanitation, food handling, and compliance with regulations |  | High |  | Inspection reports, safety review meetings, and email follow-ups | Weekly
ITS (Information Technology Services) |  |  | Sets up and maintains POS and network systems | Med | Network reliability, POS integration, and minimal downtime |  | Medium |  | Technical review meetings and system status updates | Weekly
Vendors (Sodexo & Local Businesses) |  |  | Provide food and beverage services | Med | Fair commission rates, consistent sales, and customer satisfaction |  | High |  | Vendor check-ins, sales reports, and in-person feedback sessions | Weekly
Students (Primary Users) |  |  | End users purchasing food and using the facility | Med | Affordable prices, variety, and convenience of on-campus dining |  | High |  | Surveys, suggestion forms, and social media engagement | Monthly
Faculty & Staff |  |  | Secondary users seeking convenient meal options |  | Quick, reliable access to food near workspace |  | Medium |  | Email announcements, campus newsletter updates | Monthly
Fire & Risk Management |  |  | Reviews fire safety and emergency plans |  | Compliance with fire safety and emergency response procedures |  | Medium |  | Fire safety audits, inspection reports, and documentation emails | Monthly
Parking & Security |  |  | Manages crowd control and campus safety near the site |  | Maintaining order, traffic control, and safety during peak hours |  | Low |  | Safety briefings and coordination emails | As needed / pre-event
Project Team |  |  | Plans, executes, and monitors project activities | High | Successful implementation, meeting deadlines, and learning outcomes |  | High |  | Team meetings, shared documents, and progress reports | Weekly
* | High = Stakeholder that can make things happen for the project if you have any challenges or hurdles that need to be overcome
Med = Stakeholder that may be able to help with making decisions but cannot help with broad, sweeping implementation efforts
Low = Stakeholder that does not have a lot of influence on a project and do not have the leverage to make changes to the project